## DSC
Sno | Screens | Description | Status | Fix Status | Ftec Status | Ref No | Enlighting
1 | Arrear Customer (Chit and Loan) | Arrear customer only should show the reports (In the system it is showing entire value) | Pending | Report is fine. Need to confirm that inactive customers display. |  |  | In Arrear Reports, All the active and arrear subscriptions are fetching in Excel Report
2 | Paid & Unpaid | Prize amount - Need to show only the balance amount | Pending | Fixed | 1. Reports are opening 2. Routes are fetching with numbers |  | Displays error notification
| Paid & Unpaid | Balance amount - In the report the balance showing even the customer made the payment |  | Clarified about 1 hour job schedule | Checked Few customers in both Paid / Unpaid, Fetched correct
| Paid & Unpaid | Paid/Unpaid - Amount variation need to check |  | Clarified about 1 hour job schedule
3 | Business report | Business report - Commission agent details are not showing only collection agent showing in the report |  | Fixed | Checked
4 | Divident | Divident button need to be added and can be edited in the passbook |  | Fixed - on 28 Jan 24 | Not completed (Divident button not added) | >>>>
5 | All reports | Route numbers are not showing up |  | Fixed | Checked |  | In all reports, Route shows without route number
In EXCEL reports
6 | Customer Account Summary reports | Summary report - Collection entry is not showing |  | Fixed | Partially Completed
Collection amount , O.S amount columns will show value for loans
negative o/s indicates that excess paid amount
Red indicates - Missed data
|  |  |  | Already subscription codes are displayed!? | Loan Subscription index need to display |  |  | Green indicates - Suggestion | Either Subscription name need to display in report or Loan subscription need to display in Loan subscription
7 | Customer Account Summary | Loan - Passbook entry is done but not showing the value the report (muthukumar n) - Customer details | (Related to Loan subscription) | Fixed | Not completed Beside attache the screen shot Below shown party account was displaying passbook amount but for MuthuKumar not fetching | >>>>>>
8 | Active / Inactive | active/inactive |  | Fixed | Checked
This is the screen in Dhansree product need to change like as in Thamburan screen
DHANASREE
THAMBURAN
9 | Loan subscription & Reports | report - 100,20,10(Loan subscription automatiically arrear reports) | Pending | Need confirmation of this fix. Check with customer for the actual requirement. (Closed / Legal /Active/ etc - Based on which status this should be automated) -Only in scheduled SP this can be done. |  |  | After selcting the 100days, 10months or etc scheme of Loan, Based on the loan date after finishing the loan date automatically subscriptions need to fetch in arrear status and arrear reports
10 | Chit Subscription & Reports | Based on disbursement date status should change to arrear | Pending | Need confirmation of this fix. Check with customer for the actual requirement. (Closed / Legal /Active/ etc - Based on which status this should be automated) -Only in scheduled SP this can be done. |  |  | After completing the date of scheme subscription need to change automatically to Arrear status and arrear reports
11 | Loan Subscription | Screen able edit after the submit | Pending | Fixed | Checked |  | Screen need to display dropdown list for editing after the Loan subscription
Only Modification allowed form values can be editable.
12 | Ledger | Need to align the ledger | Pending | Fixed | Not completed in Loan Subscription
>>>>>>>>>>>>>
13 | Loan Subscription | Loan ID need to display in index | Pending | Fixed | Not Completed | >>>>>
Subscription code already displayed
14 | Client Master | There is no email id and Contact person field in add new screen | Pending | Fixed | Checked |  | Need to add fields in side the screen
Contact person for company ; Email id enabled to enter
15 | Difference of STC and DS | Active client summary and Paid / Unpaid |  | Fixed | Checked
DHANSREE
THAMBURAN
16 | Transaction Collection | Need to hide all the dropdown list except Collected |  | Fixed | Checked
17 | Daily Collection Plan | Error notification displays |  | Fixed | Checked
18 | Loan Subscription | After submitting the subscription changes should not take or if any changes done that should effet in ledger too |  | Working Fine | Woking Fine
19 | Chit Subscription | Can able to change the status to previous too |  | Working fine | Working fine
20 | Loan subscription | Need to remove the below highlighted columns Coz there is no such field in subscription screen |  | Pending
21 |  | Add all the report names. It just displays the date
|  | The below attached screen shot are the downloaded excel reports of paid/unpaid, active and business etc but cann't find which report is active based on the number. |  | Pending
22 | Loan Subscription | If any customer are completing the loan period. Before 15days must indicate |  | Pending
23 | Transaction Collection / Ledger | Same type and amount are displaying only once |  | Pending
24 | Paid / Unpaid Report | Loan details are not there in excel. Only Chit details are there.
25 | Arrear Report | Closed customers are fetching from Loan Subscription
26 | Loan Subscription | If the customer going to completed subscription time before 1 month should indicate

## Completed
Sno | Screens | Description | Status | Fix Status | Ftec Status
2 | Paid & Unpaid | Prize amount - Need to show only the balance amount | Pending | Fixed | 1. Reports are opening 2. Routes are fetching with numbers | Paid Divident, Unpaid divident, Balance Payment Type need to remove
| Paid & Unpaid | Balance amount - In the report the balance showing even the customer made the payment |  | Clarified about 1 hour job schedule | Checked Few customers in both Paid / Unpaid, Fetched correct
| Paid & Unpaid | Paid/Unpaid - Amount variation need to check |  | Clarified about 1 hour job schedule
3 | Business report | Business report - Commission agent details are not showing only collection agent showing in the report |  | Fixed | Checked | Payment Type, Price amount remove
8 | Active / Inactive | active/inactive |  | Fixed | Checked
11 | Loan Subscription | Screen able edit after the submit | Pending | Fixed | Checked | Ledger - Start date and End, Balance amount date needed
14 | Client Master | There is no email id and Contact person field in add new screen | Pending | Fixed | Checked
15 | Difference DS | Active client summary and Paid / Unpaid |  | Fixed | Checked
16 | Transaction Collection | Need to hide all the dropdown list except Collected |  | Fixed | Checked
17 | Daily Collection Plan | Error notification displays |  | Fixed | Checked | Bharathi mam need to discuss with Sajeevan sir
18 | Loan Subscription | After submitting the subscription changes should not take or if any changes done that should effet in ledger too |  | Working Fine | Woking Fine
19 | Chit Subscription | Can able to change the status to previous too |  | Working fine | Working fine

## Pending
Sno | Screens | Description | Status | Fix Status As on 04Feb24 | Ftec Status | Ref No | Enlighting
4 | Divident | Divident button need to be added and can be edited in the passbook |  | Fixed by redeployment | Not completed (Divident button not added) | >>>>
5 | All reports | Route numbers are not showing up |  | Checked | Checked
6 | Customer Account Summary reports | Summary report - Collection entry is not showing |  | Fixed by redeployment and updated fix; Passbook total will show the balance to be collected for LOANS. | Partially Completed Loan Subscription need to display in Loan Subscription index
|  | Reference - |  |  |  |  | After Fixed
9 | Loan subscription & Reports | report - 100,20,10(Loan subscription automatiically arrear reports) | Pending | Fixed (job updated) |  |  | After selcting the 100days, 10months or etc scheme of Loan, Based on the loan date after finishing the loan date automatically subscriptions need to fetch in arrear status and arrear reports
10 | Chit Subscription & Reports | Based on disbursement date status should change to arrear | Pending | Fixed (job updated) |  |  | After completing the date of scheme subscription need to change automatically to Arrear status and arrear reports
12 | Ledger | Need to align the ledger | Pending | Fixed by Redeployment | Not completed in Loan Subscription
|  | Reference |  |  |  |  | After Fixing
13 | Loan Subscription | Loan ID need to display in index | Pending | Fixed by Redeployment | Not Completed | >>>>>
20 | Loan subscription | Need to remove the below highlighted columns Coz there is no such field in subscription screen |  | Payment type column is mentioned as "Collection Type" in LS / CS. Clarified. If not required then we can remove. Confirmation required.
21 |  | Add all the report names. It just displays the date
|  | The below attached screen shot are the downloaded excel reports of paid/unpaid, active and business etc but cann't find which report is active based on the number. |  | Fixed
22 | Loan Subscription | If any customer are completing the loan period. Before 15days must indicate |  | To be done
23 | Transaction Collection / Ledger | Same type and amount are displaying only once |  | Need more inputs / case study information on exact required output.
24 | Paid / Unpaid Report | Loan details are not there in excel. Only Chit details are there. |  | Need more inputs / case study information on exact required output.
25 | Arrear Report | Closed customers are fetching from Loan Subscription |  | Need more inputs / case study information on exact required output.
26 | Loan Subscription | If the customer going to completed subscription time before 1 month should indicate |  | To be done